## Slide 1: SSW-555: Agile Methods for Software Development
Scenario-based questions 4
Instructor: Dr. Nafiseh Ghorbani
Department of Systems and Enterprises
Stevens Institute of Technology

## Slide 2: Scenario 1: Minimizing Waste in Software Development
You are leading a software development team, and you've noticed that the team spends a significant amount of time building features that customers rarely use, while some key features are not receiving enough attention. How can you apply Lean Software Development principles to reduce waste in this process?

## Slide 3: Scenario 1: Minimizing Waste in Software Development
Eliminate Waste (Muda):
  Identify unnecessary features by talking to stakeholders, users, or analyzing usage data to identify which features are underused and should be removed or minimized.
  Focus on building only high-value features that directly address customer needs.
  Use Kanban boards or similar tools to visualize tasks, making it clear which features add the most value.
Continuous Improvement (Kaizen):
  Establish regular feedback loops with users to assess the value of the features delivered and continuously refine the backlog.
  Use retrospectives to reflect on the team’s processes and improve efficiency.
Just-in-Time Development:
  Adopt just-in-time development to build features when they are needed rather than speculating on future requirements.
  Prioritize features based on real-time customer feedback rather than building everything upfront.

## Slide 4: Scenario 2: Reducing Overproduction in Development
Your development team is currently building software based on a large set of initial requirements. However, the business has shifted its priorities midway through the development. How can Lean principles help in reducing overproduction and ensure the team builds only what's necessary?

## Slide 5: Scenario 2: Reducing Overproduction in Development
Build Incrementally:
  Instead of building all features upfront, break the development process into smaller, incremental releases that deliver value as soon as possible.
  Use small batches of code and deploy frequently, ensuring that each release is usable and has customer value.
Focus on Customer Feedback:
  Develop a feedback loop with customers or end-users to validate features before building unnecessary functionality.
  Involve stakeholders regularly to adjust priorities and refine requirements throughout the development process.
Pull System:
  Use a Kanban system to manage work items, ensuring that the team only pulls in work that is required at the moment, preventing overproduction of unnecessary features.

## Slide 6: Scenario 3: Improving Development Speed Without Sacrificing Quality
Your team is under pressure to deliver a new feature in a short amount of time. However, there is concern that rushing could compromise the software's quality. How can you apply Lean principles to balance speed and quality?

## Slide 7: Scenario 3: Improving Development Speed Without Sacrificing Quality
Quality Built-in (Jidoka):
  Emphasize automated testing (unit tests, integration tests, etc.) to catch issues early and ensure quality is maintained while increasing speed.
  Pair programming or code reviews can help ensure quality is built into the product as it’s developed, rather than fixing issues later.
Flow:
  Focus on streamlining the workflow by eliminating bottlenecks (e.g., wait times, unclear task handoffs, etc.).
  Use continuous integration (CI) and continuous delivery (CD) pipelines to automate repetitive tasks, reducing time spent on manual processes and speeding up development.
Empowered Teams:
  Encourage the team to take ownership of the process, allowing them to make decisions on the fly that ensure both quality and speed are maintained.

## Slide 8: Scenario 4: Managing Changing Requirements Efficiently
The requirements for your project have changed rapidly over time, and the product you're building is no longer aligning with what the business needs. How can you use Lean Software Development principles to effectively manage these changes?

## Slide 9: Scenario 4: Managing Changing Requirements Efficiently
Flexibility and Responsiveness to Change:
  Adopt an iterative and incremental development approach to enable fast adaptation to changing requirements.
  Focus on delivering value quickly, so that the team can pivot and adjust to changes with minimal wasted effort.
Continuous Improvement (Kaizen):
  Conduct regular retrospectives to assess how the team can better handle change and adapt their workflow for maximum responsiveness.
Set-based Design:
  Instead of deciding on a single solution early on, use set-based design to explore multiple options, keeping the solution open for change until enough information is gathered.

## Slide 10: Scenario 5: Optimizing Communication and Collaboration
Your software development team often faces miscommunication between developers, product managers, and designers. These miscommunications are causing delays and confusion in the project. How can Lean principles improve communication and collaboration within the team?

## Slide 11: Scenario 5: Optimizing Communication and Collaboration
Visual Management:
  Use Kanban boards or visual task boards to make the work process visible to all team members. This ensures everyone is on the same page about what needs to be done, who is responsible, and the status of tasks.
Cross-Functional Teams:
  Encourage cross-functional teams, where developers, product managers, and designers work together on the same tasks. This creates direct communication lines and reduces miscommunication.
Frequent Feedback:
  Set up short feedback loops with stakeholders and team members to clarify requirements and ensure everyone understands the direction of the project.
  Hold daily stand-ups or regular check-ins to ensure that the team aligns on priorities and challenges.

## Slide 12: Scenario 6: Managing Technical Debt
As the development team has worked on the software, technical debt has started to accumulate. There are many areas of the code that are hard to maintain and modify, causing delays in delivering new features. How can Lean principles help in managing technical debt?

## Slide 13: Scenario 6: Managing Technical Debt
Continuous Improvement (Kaizen):
  Adopt a culture of continuous improvement, where technical debt is regularly identified and addressed during each sprint or iteration. Allocate time for refactoring or resolving debt as part of the regular work process.
Set Quality Standards:
  Establish and adhere to coding standards and ensure that all new code is well-tested and well-documented to prevent additional technical debt from accumulating.
Simplicity:
  Lean emphasizes simplicity—build only what’s necessary and avoid overengineering. When technical debt is introduced, simplify the code or system design to reduce complexity and make future changes easier.
Visualize Technical Debt:
  Use visual tools like technical debt tracking boards to make it visible and ensure it’s addressed in the context of ongoing work.

## Slide 14: Scenario 7: Reducing Lead Time in Software Delivery
Your team is facing long lead times from the moment a feature request is made until it is delivered to the customer. How can Lean principles be applied to reduce this lead time?

## Slide 15: Scenario 7: Reducing Lead Time in Software Delivery
Flow:
  Identify and eliminate bottlenecks in the process to ensure smooth flow. For example, reducing waiting time between stages (design, development, testing) will minimize delays.
  Implement continuous integration to ensure that code is frequently integrated and tested, reducing the time it takes for code to move through development stages.
Work-in-Progress (WIP) Limits:
  Apply WIP limits in Kanban or similar systems to prevent overloading team members and ensure that the team focuses on finishing current tasks before starting new ones.
Prioritize Work:
  Use pull-based systems to prioritize work based on customer demand, ensuring that the team works on the most important tasks first, thus reducing lead times.

## Slide 16: Scenario 8: Value Stream Mapping (VSM) in Software Development
Your software development team is experiencing delays in feature delivery due to inefficiencies in the development process. How can you use Value Stream Mapping (VSM) to identify and resolve these issues?

## Slide 17: Scenario 8: Value Stream Mapping (VSM) in Software Development
Identify the Current State:
  Map out the entire software development process from feature request to deployment, including all steps such as requirement gathering, design, development, testing, and release.
  Include all handoffs and delays (e.g., waiting for approval, time spent in QA testing, etc.).
Visualize Bottlenecks:
  Use the value stream map to identify areas where work items are getting stuck or delayed (e.g., approval stages, manual testing bottlenecks, etc.).
  Look for non-value-added activities or unnecessary delays, such as excessive waiting times or redundant handoffs between departments.
Focus on Lead Time:
  Measure the lead time for each step of the value stream, from feature request to final delivery.
  Identify steps that are taking longer than necessary and examine ways to reduce time spent in each phase.

## Slide 18: Scenario 8: Value Stream Mapping (VSM) in Software Development
Focus on Lead Time:
  Measure the lead time for each step of the value stream, from feature request to final delivery.
  Identify steps that are taking longer than necessary and examine ways to reduce time spent in each phase.
Optimize the Process:
  Remove or improve inefficient steps—automate manual processes, improve collaboration between teams, and reduce waiting times.
  Streamline communication between product managers, developers, and QA teams to reduce handoffs and improve efficiency.
  Focus on creating continuous flow and reducing waiting times in the process to shorten the lead time and deliver features faster.
Future State Mapping:
  After identifying inefficiencies, create a future state map that outlines an optimized version of the value stream with reduced delays and waste.
  Implement and monitor the changes to ensure continuous improvement.

## Slide 19: Scenario 9: Set-Based Development in Software Design
Your development team is facing a difficult design decision and needs to choose between several different architectures for a new software feature. How can Set-Based Development (SBD) help in making this decision?

## Slide 20: Scenario 9: Set-Based Development in Software Design
Explore Multiple Options Simultaneously:
  Instead of deciding on one architecture immediately, explore multiple design options (set of possible architectures) in parallel.
  Allow each option to be developed to a certain degree, without fully committing to one solution right away.
Gather Data Through Prototyping:
  Build prototypes for each architecture to gather real data about how each approach works in practice.
  Use these prototypes to evaluate the feasibility, scalability, and performance of different designs.
Narrow Down the Set:
  Gradually eliminate less viable options based on the data gathered from prototyping and testing, refining your choices until the optimal solution is found.
  This allows you to focus on fewer solutions without locking in a final choice prematurely.

## Slide 21: Scenario 9: Set-Based Development in Software Design
Make Decisions Based on Information:
  Once sufficient information is gathered, choose the architecture that offers the best trade-offs in terms of performance, scalability, and alignment with business goals.
  This avoids making a decision based on assumptions and allows the team to choose the solution that best fits the problem at hand.
Apply Lean Principles:
  The set-based approach minimizes the risk of making costly mistakes by avoiding premature commitment to a single solution.
  It ensures that decisions are based on real data rather than speculation, improving the design process and aligning it more closely with customer and business needs.

## Slide 22: Scenario 10: Pull Systems (Kanban) in Managing Workflow
Your software development team has too many ongoing tasks, and it’s leading to delays and confusion. How can you implement a Pull System (using Kanban) to improve workflow and reduce bottlenecks?

## Slide 23: Scenario 10: Pull Systems (Kanban) in Managing Workflow
Implement a Kanban Board:
  Set up a Kanban board with columns such as “Backlog,” “To Do,” “In Progress,” “Testing,” and “Done.”
  Each task (e.g., features, bugs) is represented by a card on the board. This provides clear visibility of the workflow and allows team members to track progress at a glance.
Set Work-In-Progress (WIP) Limits:
  Define WIP limits for each stage of the process (e.g., only 3 tasks in “In Progress” at any given time).
  This prevents overloading team members and ensures that they focus on completing tasks before taking on new ones, preventing bottlenecks and task switching.
Pull Work When Capacity Allows:
  Team members pull tasks from the “To Do” column only when they have the capacity to work on them. This avoids overburdening the team with too many tasks at once.
  This ensures that each person only works on one task at a time, promoting focus and reducing context switching.

## Slide 24: Scenario 10: Pull Systems (Kanban) in Managing Workflow
Visualize Bottlenecks:
  Use the Kanban board to identify bottlenecks in the process. If tasks are piling up in a particular column (e.g., Testing), it’s an indication that the team needs to address the issue in that stage (e.g., adding more testers, automating tests).
Improve Flow:
  As tasks move from one column to the next, aim to improve the flow of work by identifying areas where delays or inefficiencies occur and resolving them.
  Regularly review the board and the WIP limits to ensure that work is moving through the system at an optimal pace and that no tasks are getting stuck.
Continuous Improvement:
  Encourage regular team meetings (e.g., daily standups) to discuss what’s working, where there are obstacles, and what can be improved.
  Use retrospectives to identify and address problems in the Kanban process, ensuring that the flow of work improves over time.

## Slide 25: Scenario 11: Value Stream Mapping in a Multi-Team Development Environment
Your company has several teams working on different components of a large software project, and you've noticed delays in coordinating work across teams. How can Value Stream Mapping help identify and resolve these coordination issues?

## Slide 26: Scenario 11: Value Stream Mapping in a Multi-Team Development Environment
Map Each Team's Value Stream:
  Create separate value stream maps for each team’s process, from the initiation of work to the delivery of the product.
  This will help visualize the individual workflows and identify areas where delays or inefficiencies are occurring in each team's process.
Identify Cross-Team Bottlenecks:
  Map the handoffs between teams to identify coordination bottlenecks—for example, one team may be waiting for input from another team, or the integration phase may be taking longer than expected.
  Look for waste created by these handoffs, such as unnecessary waiting or poor communication.
Improve Cross-Team Communication:
  Use the value stream map to streamline communication channels between teams. This might include setting up regular coordination meetings or establishing shared tools for project tracking.
  Identify if any process steps could be automated or simplified to reduce delays in passing work from one team to another.

## Slide 27: Scenario 11: Value Stream Mapping in a Multi-Team Development Environment
Optimize Overall Flow:
  Focus on creating a continuous flow of work across teams, ensuring that each handoff is as smooth and quick as possible.
  Consider whether tasks should be pulled into a team’s process rather than pushed, reducing unnecessary waiting or delays.
Align Teams to a Shared Goal:
  Ensure all teams are aligned on the same business objectives and have clear visibility into how their work contributes to the overall value stream.
  This reduces miscommunication and ensures that teams work together towards a common goal.

## Slide 28: Scenario 12: Reducing Cycle Time in Feature Development
Your development team has been struggling to deliver features in a timely manner, and stakeholders are unhappy with the long wait for new functionalities. You want to reduce the cycle time for feature development. How can you approach this problem?

## Slide 29: Scenario 12: Reducing Cycle Time in Feature Development
Define Cycle Time:
  Cycle time is the time taken to complete a task, from when the team starts working on it to when it is finished (i.e., from “In Progress” to “Done”).
Identify Bottlenecks:
  Map the team’s workflow to identify where delays occur (e.g., long wait times in development, excessive QA cycles, or deployment delays).
  Use Kanban boards or similar tools to visualize the tasks and pinpoint areas where work is getting stuck.
Streamline Workflows:
  Limit Work-in-Progress (WIP): By limiting the number of tasks being worked on at any given time, you prevent the team from multitasking and reduce delays.
  Encourage the team to focus on finishing tasks before starting new ones, improving the flow of work.

## Slide 30: Scenario 12: Reducing Cycle Time in Feature Development
Automate Repetitive Tasks:
  Automate testing, integration, and deployment pipelines to reduce the time spent on manual steps and improve the speed of delivering features.
  Introduce Continuous Integration/Continuous Deployment (CI/CD) to ensure that features can be deployed quickly and reliably.
Improve Collaboration:
  Encourage closer collaboration between developers, testers, and other stakeholders, ensuring smoother transitions between stages.
  Hold daily stand-ups to ensure everyone is aligned on priorities and roadblocks.
Analyze Data and Continuously Improve:
  Use metrics to track cycle time over multiple sprints to identify patterns and further reduce delays.
  Hold retrospectives to continuously improve team practices and optimize cycle time.

## Slide 31: Scenario 13: Managing Lead Time in a Large Project
You’re managing a large software project, and the project has multiple teams working on different features. However, you’re concerned because the lead time from feature request to delivery is much longer than expected. How can you manage and reduce lead time across teams?

## Slide 32: Scenario 13: Managing Lead Time in a Large Project
Define Lead Time:
  Lead time is the total time it takes for a customer’s request to be fulfilled, from the moment the request is made until the feature is deployed and live.
Map the Entire Process:
  Use Value Stream Mapping (VSM) to visualize the entire workflow from the point when a request is made until the feature is delivered. This will help identify which parts of the process are taking the longest.
Prioritize Features:
  Work with stakeholders to prioritize features based on business value to ensure that the most important features are delivered first.
  Break down large features into smaller, manageable tasks to ensure that work can be delivered incrementally, reducing the time it takes to deliver meaningful functionality.
Shorten Wait Times:
  Identify and reduce waiting times between stages (e.g., requirements gathering, development, testing) by improving communication and reducing handoff delays between teams.
  Use Kanban boards to visualize work and manage flow, so that no team is waiting too long for work to be handed off.

## Slide 33: Scenario 13: Managing Lead Time in a Large Project
Implement Pull Systems:
  Implement a pull system (Kanban) to ensure that teams pull work only when they have the capacity to handle it. This prevents overloading teams and ensures steady progress.
Automate Where Possible:
  Automate testing, code reviews, and deployments to reduce time spent on repetitive tasks and speed up the delivery process.
  Ensure continuous integration (CI) and continuous delivery (CD) practices are in place to streamline releases.
Track Lead Time:
  Use metrics to track lead time at different stages of the process. Look for trends and identify where you can make adjustments to speed up the process.
Improve Communication:
  Enhance communication across all teams involved to avoid delays due to misunderstandings or waiting for information. Daily standups and regular check-ins between teams can help reduce delays.